HireHub

The Professional Network for Maritime Crew

PROJECT STATUS TRACKER

Living Document — Updated at Each Phase Transition

| Current phase | Phase 2 → Phase 3 |
| --- | --- |
| Last updated | April 5, 2026 |
| Deliverables completed | 15 / 23 |
| Overall progress | 65% |

This document is the single source of truth for the HireHub project.It is updated after each work session and carried forward to the next channel.

# 1. Master task list — Full stack overview

Every deliverable across all 5 phases, with current status. This is the authoritative checklist — update the status column after each work session.

## Phase 1 — Foundation & information architecture

| # | Deliverable | Status | Output file / location | Notes |
| --- | --- | --- | --- | --- |
| 1.1 | User personas (Seafarer, Shipowner, Agent) | DONE | Visual Report Fig.2-4 | 3 personas with pain points, goals, features |
| 1.2 | Core platform flow diagram | DONE | Visual Report Fig.5 | 5-step flow: profile → search → shortlist → agent → deploy |
| 1.3 | Legal compliance assessment (PH law) | DONE | HireHub_Legal_Compliance_Assessment.docx | 9 PASS + 1 CAUTION. Verdict: viable. |
| 1.4 | Information architecture / sitemap | DONE | Visual Report Fig.6 | 16 pages, role-based visibility, interactive |
| 1.5 | User stories & feature priorities | DONE | Embedded in personas + IA | Prioritized per persona in persona cards |
| 1.6 | Seafarer Consent & Data Processing Agreement | DONE | Seafarer_Consent_Agreement_FULL_PRO.docx | Full legal draft, 17 sections + 3 annexes |

## Phase 2 — UX/UI design (LinkedIn-style)

| # | Deliverable | Status | Output file / location | Notes |
| --- | --- | --- | --- | --- |
| 2.1 | Design system (colors, typography, components) | DONE | Visual Report Fig.13 | Full token spec + component library |
| 2.2 | Mockup: Seafarer profile | DONE | Visual Report Fig.7 | Hero card, sea service, certs, AI score, sidebar |
| 2.3 | Mockup: Talent search | DONE | Visual Report Fig.8 | Filter panel + candidate cards + AI ranking |
| 2.4 | Mockup: Shortlist & pipeline | DONE | Visual Report Fig.9 | Pipeline tabs + agent integration panel |
| 2.5 | Mockup: Manning agent dashboard | DONE | Visual Report Fig.10 | Incoming shortlists + deployment pipeline |
| 2.6 | Mockup: Home feed | DONE | Visual Report Fig.11 | LinkedIn-style 3-column feed layout |
| 2.7 | Mockup: Messaging / InMail | DONE | Visual Report Fig.12 | Thread list + chat + shortlist context banner |
| 2.8 | Full visual report (all mockups + commentary) | DONE | HireHub_Full_Visual_Report.docx | 13 figures, 8 chapters, 1.5MB |
| 2.9 | Detailed spec report (component breakdowns) | DONE | HireHub_Project_Deliverables_Report.docx | Tables with every component specified |

## Phase 3 — Interactive prototype

| # | Deliverable | Status | Output file / location | Notes |
| --- | --- | --- | --- | --- |
| 3.1 | Database schema / ERD | NEXT | — | Entities: Users, Profiles, SeaService, Certs, Companies, Shortlists, Messages, AIScores |
| 3.2 | API specifications (RESTful endpoints) | PLANNED | — | Auth, profile CRUD, search, matching, shortlist, messaging, agent integration |
| 3.3 | Clickable React prototype | PLANNED | — | Interactive demo connecting all 6 screens. For investors + early users. |
| 3.4 | Formal legal opinion (PH maritime law firm) | PLANNED | — | Written certification from Del Rosario or similar |

## Phase 4 — MVP development

| # | Deliverable | Status | Output file / location | Notes |
| --- | --- | --- | --- | --- |
| 4.1 | Frontend build (React, responsive) | PLANNED | — | Based on design system + mockups |
| 4.2 | Backend & AI engine (matching, verification) | PLANNED | — | Node.js/Python, PostgreSQL, AI models |
| 4.3 | Testing & QA | PLANNED | — | User testing, bug fixes, performance |

## Phase 5 — Launch & growth

| # | Deliverable | Status | Output file / location | Notes |
| --- | --- | --- | --- | --- |
| 5.1 | Go-to-market strategy & execution | PLANNED | — | Philippines first, then UA/RO/BG expansion |
| 5.2 | Metrics, analytics & iteration | PLANNED | — | KPIs, dashboards, user feedback loops |

# 2. Files inventory

All project files produced to date, with descriptions and locations.

| File name | Type | Contents |
| --- | --- | --- |
| Seafarer_Consent_Agreement_FULL_PRO.docx | Legal document | 17-section consent & data processing agreement with AI annex, security annex, data schedule |
| HireHub_Legal_Compliance_Assessment.docx | Legal analysis | Philippine law compliance check: 9 PASS + 1 CAUTION, verdict, safeguards, legislation references |
| HireHub_Project_Deliverables_Report.docx | Spec document | Full specs with component breakdown tables for all 6 mockups, design system, IA |
| HireHub_Full_Visual_Report.docx | Visual report | 13 embedded images with captions and commentary. The complete visual bible. |
| HireHub_Project_Status_Tracker.docx | THIS FILE | Living tracker. Updated at each phase transition. Carry forward to next channel. |

# 3. What has been built — Summary

## 3.1 User personas

Three detailed personas created with demographics, key metrics, pain points, platform goals, and required features:

| Persona | Role | Key metric | Primary need |
| --- | --- | --- | --- |
| Juan Dela Cruz | Seafarer (3rd Officer) | $1,800/mo, 4 yrs service | Visibility to global employers, verified badge |
| Nikos K. | Shipowner (Fleet Mgr) | 12 vessels, 240 crew | Search talent directly, reduce hiring to 5 days |
| Manning Agency | Manning Agent (DMW) | 8 principals, 500 depl/yr | Receive pre-vetted candidates from owners |

## 3.2 Legal compliance

Full assessment against R.A. 8042/10022 (Migrant Workers Act), R.A. 12021 (Magna Carta of Filipino Seafarers), R.A. 10173 (Data Privacy Act). Result: 9 tests PASSED, 1 CAUTION (AI matching framing). Verdict: MODEL IS LEGALLY VIABLE.

## 3.3 Information architecture

16 pages/features mapped across 3 user roles. LinkedIn-inspired navigation: Home Feed, Jobs/Talent Search, Messaging, Notifications, Profile. Role-based access with premium tier differentiation.

## 3.4 UI/UX mockups (6 screens)

| Screen | Key components |
| --- | --- |
| Seafarer Profile | Hero card (banner + avatar + verified badge), sea service timeline, certificates with Valid/Expiring badges, skills tags, AI score sidebar, availability grid, profile completeness bar |
| Talent Search | Filter panel (rank, vessel, nationality, availability, credentials), candidate cards with AI score rings, sort by AI match/service/availability, AI matching active banner |
| Shortlist & Pipeline | Pipeline tabs (Shortlisted/Under Review/Sent to Agent), candidate rows with checkboxes, Compare + Forward to Agent buttons, agent integration panel with DMW license |
| Agent Dashboard | Agency header with DMW license, 4 metric cards, incoming shortlists from Greek owners (Tsakos, Diana, Capital Ship), deployment pipeline (Received/Vetting/Contract/Deployment) |
| Home Feed | 3-column LinkedIn layout: mini profile + nav, post feed (training + career milestones), trending topics + latest jobs from Greek shipping companies |
| Messaging | Thread list + active chat, shortlist context banner, sample conversation showing legal flow (owner mentions forwarding to manning agent) |

## 3.5 Design system

Complete specification: 17 colors (primary, semantic, neutrals), 6-level typography scale, 7-step spacing system, 4 border radius tokens, 4 button styles, 6 badge variants, avatar sizes, card components, metric cards, AI score rings with 3 color tiers (green 85+, blue 70-84, amber <70).

# 4. Next steps — Phase 3 action plan

The following deliverables are queued for Phase 3. When starting the next work session, begin with item 3.1 (Database Schema).

## 4.1 Database schema / ERD

Design the complete entity-relationship diagram covering all platform data. This is the foundation for the API and prototype.

| Entity | Key fields |
| --- | --- |
| Users | id, email, password_hash, role (seafarer/owner/agent), created_at, last_active |
| SeafarerProfiles | user_id, full_name, nationality, rank, photo_url, bio, verified_status, profile_completeness |
| SeaService | profile_id, vessel_name, vessel_type, dwt, flag_state, rank_held, company, start_date, end_date |
| Certificates | profile_id, cert_type (COC/STCW/COP), issuing_authority, issue_date, expiry_date, verified, doc_url |
| Companies | id, name, type (owner/agent), dmw_license, country, fleet_size, logo_url |
| Shortlists | id, owner_id, title, vessel_context, agent_id, created_at, status |
| ShortlistCandidates | shortlist_id, profile_id, ai_score, status (shortlisted/review/sent), added_at |
| Messages | id, thread_id, sender_id, recipient_id, body, sent_at, read_at |
| AIScores | profile_id, search_criteria_hash, score, computed_at |

## 4.2 API specifications

RESTful API endpoints to be designed for all platform operations:

| Endpoint group | Methods | Operations |
| --- | --- | --- |
| Auth | POST | Register, Login, Refresh token, Password reset, OAuth |
| Profiles | GET/POST/PUT/DEL | Create profile, Update, Get by ID, Upload photo, Upload certificate, Set availability |
| Search | GET/POST | Search candidates (filters), AI match scoring, Autocomplete suggestions |
| Shortlists | GET/POST/PUT/DEL | Create shortlist, Add/remove candidates, Update status, Forward to agent |
| Messaging | GET/POST | List threads, Get thread messages, Send message, Mark as read |
| Companies | GET/POST/PUT | Company profile CRUD, DMW license verification, Fleet management |
| Analytics | GET | Profile views, Shortlist counts, Search appearances, Market insights |

## 4.3 Clickable React prototype

Interactive prototype connecting all 6 screens into a navigable demo. Navigation flow: Home Feed → Talent Search → Seafarer Profile → Add to Shortlist → Shortlist & Pipeline → Forward to Agent → Agent Dashboard. Ready for investor presentations and early user testing.

## 4.4 Formal legal opinion

Engage a Philippine maritime law firm (e.g., Del Rosario & Del Rosario, or Sapalo Velez Bundang & Bulilan) for formal written legal opinion certifying that HireHub’s operational model falls outside the definition of recruitment and placement under Philippine law. This is a prerequisite before any public launch.

# 5. How to use this tracker

This document is designed as a living project tracker. Follow these rules:

- At the start of each new work session / channel: Share this document with the instruction “This is our project status tracker. Continue from the NEXT item.”

- After completing a deliverable: Update the status from NEXT/PLANNED to DONE, add the output file name, and add any relevant notes.

- After each session: Re-export this document with updated statuses and carry it to the next channel.

- The NEXT item is always the first thing to work on when starting a new session.

- Section 3 (What has been built) provides context for anyone joining the project mid-stream.

- Section 4 (Next steps) provides detailed specs for what comes next, so work can begin immediately.

NEXT SESSION INSTRUCTION

Copy-paste this into the next channel: "This is the HireHub Project Status Tracker. The project name is HireHub (maritime professional network, LinkedIn for seafarers). We are transitioning from Phase 2 to Phase 3. The next deliverable is item 3.1: Database Schema / ERD. Please review the tracker and continue building from where we left off. All previous mockups, personas, legal assessment, and design system are documented in the companion files listed in Section 2."

© 2026 HireHub — All rights reserved | Confidential