HireHub

The Professional Network for Maritime Crew

PROJECT STATUS TRACKER

| Current phase | Phase 2 → Phase 3 |
| --- | --- |
| Last updated | April 5, 2026 |
| Deliverables completed | 16 / 25 |
| Overall progress | 64% |
| Tech stack | Java · Vue.js · Python |

Living Document — Updated at Each Phase Transition

Confidential — All rights reserved

# 1. Technology stack

The HireHub platform follows a three-tier architecture aligned with the development team’s standards. All technology choices are production-grade and enterprise-ready.

| Layer | Technology | Details |
| --- | --- | --- |
| Backend | Java / Spring Boot 3 | REST API, Spring Security (JWT), Spring Data JPA, Hibernate. PostgreSQL 15+ database. Maven build. |
| Frontend | Vue.js 3 | Composition API, Vue Router, Pinia state management. Responsive SPA following HireHub Design System. Axios for API calls. |
| AI Engine | Python / FastAPI | Separate microservice. AI matching, credential verification (CV), NLP, recommendation engine. Communicates with backend via REST. |
| Database | PostgreSQL 15+ | 19 tables, UUID primary keys, pg_trgm for fuzzy search, JSONB for flexible data. Schema v1 complete. |
| Infrastructure | Azure | Azure App Service (backend + frontend), Azure Database for PostgreSQL, Azure Blob Storage (documents/photos), Azure Container Instances (AI microservice). |
| Version control | GitHub (Private) | Repository: Apostolos-Bizou/HireHub. Main branch, feature branches per deliverable. |

# 2. Master task list

Every deliverable across all 5 phases with current status. This is the authoritative checklist.

## Phase 1 — Foundation & information architecture

| # | Deliverable | Status | Output / notes |
| --- | --- | --- | --- |
| 1.1 | User personas (Seafarer, Shipowner, Manning Agent) | DONE | 3 personas with demographics, pain points, goals, features |
| 1.2 | Core platform flow diagram | DONE | 5-step flow: profile → search → shortlist → agent → deploy |
| 1.3 | Legal compliance assessment (PH law) | DONE | 9 PASS + 1 CAUTION. Verdict: legally viable |
| 1.4 | Information architecture / sitemap | DONE | 16 pages, role-based visibility, interactive |
| 1.5 | User stories & feature priorities | DONE | Prioritized per persona |
| 1.6 | Seafarer Consent & Data Processing Agreement | DONE | Full legal draft, 17 sections + 3 annexes |

## Phase 2 — UX/UI design

| # | Deliverable | Status | Output / notes |
| --- | --- | --- | --- |
| 2.1 | Design system (colors, typography, components) | DONE | Full token spec + component library |
| 2.2 | Mockup: Seafarer profile | DONE | Hero card, sea service, certs, AI score, sidebar |
| 2.3 | Mockup: Talent search | DONE | Filter panel + candidate cards + AI ranking |
| 2.4 | Mockup: Shortlist & pipeline | DONE | Pipeline tabs + agent integration panel |
| 2.5 | Mockup: Manning agent dashboard | DONE | Incoming shortlists + deployment pipeline |
| 2.6 | Mockup: Home feed | DONE | LinkedIn-style 3-column feed layout |
| 2.7 | Mockup: Messaging / InMail | DONE | Thread list + chat + shortlist context banner |
| 2.8 | Full visual report | DONE | 13 figures, 8 chapters |
| 2.9 | Detailed spec report (component breakdowns) | DONE | Tables with every component specified |

## Phase 3 — Technical architecture & prototype

| # | Deliverable | Status | Output / notes |
| --- | --- | --- | --- |
| 3.1 | Database schema / ERD (PostgreSQL) | DONE | 19 tables, full SQL schema, ERD diagram. GitHub: database/ |
| 3.2 | API specifications (RESTful / OpenAPI 3.0) | NEXT | Spring Boot endpoints. Auth, profiles, search, shortlists, messaging, agents |
| 3.3 | AI microservice specification (Python/FastAPI) | PLANNED | Matching engine, credential verification, NLP, scoring API |
| 3.4 | Clickable Vue.js prototype | PLANNED | Interactive demo connecting all 6 screens. Investor-ready. |
| 3.5 | Formal legal opinion (PH maritime law firm) | PLANNED | Written certification from Del Rosario or similar |

## Phase 4 — MVP development

| # | Deliverable | Status | Output / notes |
| --- | --- | --- | --- |
| 4.1 | Backend build (Java / Spring Boot 3) | PLANNED | REST API, JWT auth, Spring Data JPA, PostgreSQL |
| 4.2 | Frontend build (Vue.js 3, responsive SPA) | PLANNED | Composition API, Pinia, Vue Router, Design System implementation |
| 4.3 | AI microservice build (Python / FastAPI) | PLANNED | Matching engine, credential CV, NLP scoring |
| 4.4 | Azure deployment & CI/CD | PLANNED | App Service, PostgreSQL, Blob Storage, Container Instances |
| 4.5 | Testing & QA | PLANNED | Unit tests, integration tests, UAT, performance |

## Phase 5 — Launch & growth

| # | Deliverable | Status | Output / notes |
| --- | --- | --- | --- |
| 5.1 | Go-to-market strategy & execution | PLANNED | Philippines first, then UA/RO/BG expansion |
| 5.2 | Metrics, analytics & iteration | PLANNED | KPIs, dashboards, user feedback loops |

# 3. Architecture overview

HireHub follows a microservices-oriented architecture with three main components communicating via REST APIs.

### System components

| Component | Technology | Responsibilities |
| --- | --- | --- |
| API Gateway / Backend | Java 21 + Spring Boot 3 | Authentication (JWT), authorization (role-based), profile CRUD, search orchestration, shortlist management, messaging, agent integration, data validation, business logic |
| Frontend SPA | Vue.js 3 + Vite | Role-based UI rendering (Seafarer/Shipowner/Agent views), reactive components, Design System implementation, API consumption via Axios, responsive layout |
| AI Microservice | Python 3.12 + FastAPI | AI matching engine (candidate-to-criteria scoring), certificate verification (OCR + anomaly detection), NLP for profile parsing, recommendation engine, bias auditing |
| Database | PostgreSQL 15+ | 19 tables (see schema v1). UUID PKs, pg_trgm fuzzy search, JSONB for AI score breakdowns, audit logging, consent tracking |
| Object Storage | Azure Blob Storage | Seafarer photos, certificate scans, CV documents, company logos. Secure signed URLs for access. |
| Hosting | Azure | App Service (backend), Static Web Apps or App Service (frontend), Container Instances (AI), Database for PostgreSQL (managed) |

### Data flow

Vue.js Frontend  →  Spring Boot API  →  PostgreSQL

Spring Boot API  ↔  Python AI Microservice  (REST, async scoring)

# 4. Files inventory

All project files produced to date. GitHub repository: Apostolos-Bizou/HireHub

| File | Location | Contents |
| --- | --- | --- |
| HireHub_Database_Schema_v1.sql | database/ | 19 tables, PostgreSQL 15+, enums, indexes, triggers, audit log |
| Seafarer_Consent_Agreement_FULL_PRO.docx | docs/legal/ | 17-section consent & data processing agreement + 3 annexes (AI, security, data schedule) |
| YourHive_Legal_Compliance_Assessment.docx | docs/legal/ | Philippine law compliance: 9 PASS + 1 CAUTION, verdict, safeguards |
| HireHub_Project_Deliverables_Report.docx | docs/reports/ | Full specs with component breakdown tables for all 6 mockups |
| HireHub_Full_Visual_Report.docx | docs/reports/ | 13 embedded figures with captions and design commentary |
| HireHub_Project_Status_Tracker_v2.docx | docs/reports/ | This document. Living tracker with tech stack alignment. |

# 5. GitHub repository structure

Target repository structure when Phase 4 is complete:

| Path | Purpose |
| --- | --- |
| docs/legal/ | Legal documents (consent agreement, compliance assessment) |
| docs/reports/ | Project reports (visual report, deliverables, tracker) |
| database/ | SQL schema, migrations, seed data |
| api/ | OpenAPI 3.0 specs, endpoint documentation |
| backend/ | Java / Spring Boot 3 application |
| frontend/ | Vue.js 3 SPA application |
| ai-service/ | Python / FastAPI AI microservice |
| prototype/ | Clickable Vue.js prototype (Phase 3.4) |
| infrastructure/ | Azure deployment configs, Docker, CI/CD |

# 6. Next steps — Phase 3 action plan

## 6.1 API specifications (item 3.2)

RESTful API endpoints documented in OpenAPI 3.0 format. Spring Boot controller structure. Covers all platform operations.

| Endpoint group | Methods | Operations |
| --- | --- | --- |
| Auth | POST | Register, Login, Refresh JWT, Password reset, OAuth 2.0 |
| Profiles | GET/POST/PUT/DEL | CRUD, photo upload, certificate upload, set availability, update preferences |
| Search | GET/POST | Filter candidates, AI match scoring (calls Python microservice), autocomplete |
| Shortlists | GET/POST/PUT/DEL | Create, add/remove candidates, update status, forward to agent |
| Messaging | GET/POST | List threads, get messages, send message, mark as read |
| Companies | GET/POST/PUT | Company CRUD, DMW license verification, fleet management |
| Analytics | GET | Profile views, shortlist counts, search appearances, market insights |
| AI Service (internal) | POST | Score candidates, verify certificates, parse CV, bias audit |

## 6.2 AI microservice specification (item 3.3)

Python/FastAPI microservice handling all AI/ML workloads. Called by the Spring Boot backend via internal REST.

| Capability | Description |
| --- | --- |
| Candidate matching | Score seafarer profiles against search criteria (rank, vessel type, experience, certs, availability). Returns 0–100 score with criteria breakdown JSON. |
| Credential verification | OCR + anomaly detection on uploaded certificate scans. Flags suspicious documents. Sets ai_verified status. |
| CV/profile parsing | NLP extraction of structured data from uploaded CVs. Auto-populates sea service, certificates, skills. |
| Recommendation engine | Career recommendations for seafarers (premium). Cert gap analysis, promotion path, salary benchmarks. |
| Bias auditing | Periodic audit of AI outputs for discrimination by nationality, age, gender. Required by Consent Agreement Section 6 and Annex A. |

## 6.3 Vue.js prototype (item 3.4)

Interactive prototype connecting all 6 screens into a navigable demo. Navigation flow: Home Feed → Talent Search → Seafarer Profile → Add to Shortlist → Shortlist & Pipeline → Forward to Agent → Agent Dashboard. Ready for investor presentations and early user testing.

# 7. Session instructions

Copy-paste the following into the next Claude channel or developer handoff:

This is the HireHub Project Status Tracker. Project: HireHub — maritime professional network (LinkedIn for seafarers). Tech stack: Java/Spring Boot 3 (backend), Vue.js 3 (frontend), Python/FastAPI (AI microservice), PostgreSQL 15+ (database), Azure (infrastructure). GitHub: Apostolos-Bizou/HireHub (private). We are transitioning from Phase 2 to Phase 3. The next deliverable is item 3.2: API Specifications (OpenAPI 3.0 for Spring Boot). Please review the tracker and continue building. All previous deliverables are documented in the companion files listed in Section 4.

© 2026 HireHub — All rights reserved | Confidential